## Sheet1
Day | Topics (unchanged order) | Build-Along Tasks (E-commerce) | Plain-language explanation
1 | Quick HTML/CSS/JS recap + DOM |  | We quickly revisit how web pages are built so our tests can find and read things like buttons, prices, and messages.
2 | Core Java recap – control flow, strings, OOP |  | We refresh Java so everyone can comfortably read and write test code.
3 | Collections & Exceptions recap + Intro to test concepts |  | We review lists/maps and error handling and tie them to test ideas like test cases and bugs.
4 | Manual Testing Fundamentals; SDLC/STLC |  | We write clear scenarios for the store: login/guest checkout, browse, add to cart, and checkout—no coding yet.
5 | Automation concepts; Selenium architecture & setup | Scaffold repo (Maven) → add dependencies (Selenium, WebDriverManager, TestNG, Jackson, JDBC, RestAssured, Allure/Extent). Create config (env, creds, timeouts). Implement DriverManager, BrowserFactory, ConfigLoader. Smoke check: open storefront URL. | We create the project, add required libraries, set basic settings, and run a tiny script to open the shop’s home page.
6 | Locators; WebDriver commands; element interactions | Create Page Objects: LoginPage (or Guest), ProductListPage (category/search results). Implement BasePage, ElementActions. Tests: login/continue as guest; navigate to a category; assert product tiles are visible with price/title. | We teach the code to click and type: log in or continue as guest, open a category, and check products appear.
7 | Test frameworks overview (TestNG/Maven); basic scripts | Add BaseTest, TestNG suite XML, groups (smoke, regression). Implement first happy-path test: login/guest → product list visible. Simple parallel on/off. | We organize tests to run as a named suite like ‘smoke’, so one command runs the happy path.
8 | Waits, alerts, frames, windows | Add WaitUtils (explicit waits); helpers for pop-ups/iframes/windows (e.g., newsletter modal, size chart iframe). Extend POs: ProductDetailPage, CompareProductsPage (optional). Tests: open product detail, add to compare, handle modals/new tabs if present. | We make tests patient and able to handle pop-ups or new tabs while moving from list to product details.
9 | Advanced Selenium: Actions, JS Executor, file up/down, screenshots | Add ActionsUtil and JsUtil; listener for screenshot-on-failure. Tests: hover over mega-menu; drag price slider; JS click fallback for stubborn elements; download size guide or a sample PDF if available. | We add ‘power moves’ like hover and slider drag, and we capture screenshots automatically when something fails.
10 | TestNG annotations; DataProviders; parameterization | Create DataProviders from CSV/JSON for category/brand/price/sort combinations. Support -Denv to switch dev/qa. Add RetryAnalyzer; tag tests (smoke/regression). | We run the same test with different products and settings and switch environments without changing code.
11 | Maven structure; build & run tests | Add Maven profiles (dev, qa, ci); Surefire/Failsafe; cross-browser hooks (Chrome/Firefox). CLI commands to run smoke/regression suites. | We run tests from the command line, pick the browser, and prepare runs for any machine.
12 | Framework components – POM, utilities, base classes | Refactor POM layers; add CommonAssertions, TestDataLoader, RandomDataUtil. Build reusable flows: loginOrGuest, searchOrNavigateToCategory, addToCart(productId). | We clean up and reuse code so adding new tests is faster and safer.
13 | Framework consolidation & utilities (no mini-project) | Integrate Allure/Extent with screenshots/logs; define error taxonomy; add a ‘flaky’ quarantine tag; health check (ping home page) before test runs. | We add rich reports, mark flaky tests, and check the store is up before starting.
14 | SQL basics & CRUD ops for test data | Provision DB (H2/MySQL). Tables: products, inventory, carts, orders, coupons. Seed baseline data. Implement DbUtil/DAO. | We set up a simple database so tests can create/read products, carts, orders, and coupons as needed.
15 | Data validation with SQL in automation scripts | After UI checkout, assert orders table has the new order and inventory decreased; verify coupon application if used. Build a UI↔DB reconciliation helper. | We double-check that what we did in the UI (buying something) truly updated the database.
16 | API testing basics – HTTP/JSON/XML, Postman | Identify endpoints: GET /products, GET /products/{id}, POST /cart, POST /checkout, GET /orders/{id}. Create Postman sanity; RestAssured base spec (auth, base URI, logging). | We learn the store’s APIs, try them in Postman, then prepare code to test them.
17 | API automation using RestAssured | Automate: list/filter products, fetch details, add to cart, checkout, check order status; JSON schema validation. Link API↔UI: create cart via API, verify in UI (or vice versa). | We automate API calls and connect them with UI tests so both sides confirm each other.
18 | CI/CD integration – Jenkins/GitHub Actions (theory/demo only) | Theory & demo only: Trainer shows a ready pipeline on a sample repo (not this project): checkout, cache deps, headless smoke run, publish Allure/Extent, store artifacts, basic matrix, and notifications. No pipeline/config changes are made to the class project. | We watch how pipelines work on a sample project and understand the steps, but we don’t set up CI/CD for our framework.
19 | Review of automation + API concepts | Refactor for stability; improve locators and waits; code review checklist. Finalize README, Runbook, Env matrix, ‘How to add a new test’. | We tidy the code and document how to run and extend it so the team can continue smoothly.
20 | Final E2E validation & sign-off (same use case) | Full E2E: login/guest → browse/filter/sort → product detail → add to cart → apply coupon → checkout → order confirmation. Collect metrics (pass %, duration); KT & backlog. | We run the full shopping journey like a real user, check results, and hand over with clear next steps.